## Backlog
Task ID | Theme (Epic) | Capability (Feature) | Sub-capability (Story) | Task | Description | Acceptance criteria | Size | Priority | Dependencies | Owner role | Phase | Status
FND-001 | Foundation & ABC Modernization | Metadata/Config Model | Define config model | Spec: author metadata/config model (.md) | Define config entities: source, target, load, transform, DQ rule, recon rule, masking rule, dependency. | Spec reviewed and approved; covers all framework config objects and ABC linkage. | M | Must | - | Architect | Foundation | Not Started
FND-002 | Foundation & ABC Modernization | Metadata/Config Model | Define config model | Design Delta control tables (DDL) | Physical control tables for the config registry and their relationship to existing ABC tables. | DDL created in Unity Catalog; FKs/keys defined; aligns with ABC schema. | M | Must | FND-001 | Data Engineer | Foundation | Not Started
FND-003 | Foundation & ABC Modernization | Metadata/Config Model | Config runtime | Implement config loader + validator | Typed config loader with schema validation and helpful errors. | Loads sample config; rejects invalid config with clear messages; unit-tested. | M | Must | FND-002 | Data Engineer | Foundation | Not Started
FND-004 | Foundation & ABC Modernization | Metadata/Config Model | Config runtime | Seed example P&C configs | Example configs for one policy feed and one harmonization transform. | Configs load and drive a sample run end to end. | S | Should | FND-003 | Data Engineer | Foundation | Not Started
FND-005 | Foundation & ABC Modernization | Metadata/Config Model | Config governance | Config versioning + change audit | Version metadata changes and record who/when/what to ABC. | Edits are versioned; change history queryable in ABC. | M | Should | FND-002 | Data Engineer | Foundation | Not Started
FND-010 | Foundation & ABC Modernization | ABC SDK | ABC interface | Spec: ABC SDK interface (.md) | Define start_run/end_run/log_balance/log_dq/log_exception/log_cost contract. | Interface signed off; mapped to existing ABC tables. | S | Must | FND-001 | Architect | Foundation | Not Started
FND-011 | Foundation & ABC Modernization | ABC SDK | ABC interface | Implement ABC SDK (workspace Python modules) | Reusable SDK wrapping existing ABC Delta tables; replaces direct table writes. | SDK delivered as workspace Python modules; writes verified against ABC tables. | L | Must | FND-010 | Data Engineer | Foundation | Not Started
FND-012 | Foundation & ABC Modernization | ABC SDK | Notebook modernization | Migrate existing ABC notebooks to SDK | Refactor current ABC-interfacing notebooks to call the SDK (real environment). | Notebooks use SDK; behavior parity with current ABC logging. | L | Must | FND-011 | Data Engineer | Build (Paid) | Not Started
FND-013 | Foundation & ABC Modernization | ABC SDK | Quality | Unit tests for ABC SDK | Cover run lifecycle, balance, DQ, exception, cost logging. | Coverage > 80% on SDK; tests pass in CI. | M | Must | FND-011 | QA | Foundation | Not Started
FND-014 | Foundation & ABC Modernization | ABC SDK | Quality | Backward-compat check vs ABC schema | Confirm SDK writes match existing ABC schema/consumers. | No breaking change to existing ABC consumers. | S | Must | FND-011 | Data Engineer | Foundation | Not Started
FND-020 | Foundation & ABC Modernization | Core Control Skills | Self-governance | Self-Review skill | Agent validates generated artifacts against standards before submitting. | Generated artifacts pass a standards checklist; violations flagged. | M | Should | FND-010 | ML/AI Engineer | Build (Paid) | Not Started
FND-021 | Foundation & ABC Modernization | Core Control Skills | Self-governance | Confidence Scoring | Attach confidence to agent outputs; route low-confidence to human. | Each output carries a confidence score; threshold routes to HITL. | M | Should | FND-020 | ML/AI Engineer | Build (Paid) | Not Started
FND-022 | Foundation & ABC Modernization | Core Control Skills | Self-governance | Cost Tracking skill | Capture per-run DBU/time/Genie-session consumption to ABC. | Consumption metrics logged per run; queryable for FinOps. | M | Must | FND-011 | Data Engineer | Foundation | Not Started
FND-023 | Foundation & ABC Modernization | Core Control Skills | Self-governance | Structured Logging + trace IDs | Standardized run/event logging with correlation/trace IDs to ABC. | All framework steps emit structured logs with trace IDs. | S | Must | FND-011 | Data Engineer | Foundation | Not Started
FND-030 | Foundation & ABC Modernization | Repo & Standards | Scaffolding | Repo / workspace-files layout | Workspace / Git-folder layout and dependency conventions (no wheel). | Source organized as workspace files; CI hook runs checks. | S | Must | - | Platform/DevOps | Foundation | Not Started
FND-031 | Foundation & ABC Modernization | Repo & Standards | Standards | Coding standards + design principles doc | Modularity, strategy/factory, DI, idempotency, naming conventions. | Doc published; adopted as review checklist. | S | Must | FND-030 | Architect | Foundation | Not Started
FND-032 | Foundation & ABC Modernization | Repo & Standards | Test harness | Test framework setup | pytest + Spark serverless test harness for transforms and rules. | Sample test runs locally and in CI. | M | Must | FND-030 | QA | Foundation | Not Started
ING-001 | Ingestion Framework | Engine Abstraction | Framework design | Spec: ingestion framework (.md) | Config contract, engine selector, capability matrix for ingestion. | Spec approved; covers batch/stream, declarative/non-declarative, append/SCD2. | S | Must | FND-001 | Architect | Foundation | Not Started
ING-002 | Ingestion Framework | Engine Abstraction | Engine selector | Design declarative vs non-declarative selector | Abstraction so one config targets Lakeflow DP or Structured Streaming/batch. | Selector switches engine by config; documented. | M | Must | ING-001 | Architect | Build (Paid) | Not Started
ING-010 | Ingestion Framework | Batch Load | Full load | Batch full-load reader to bronze (non-declarative) | Generic batch reader writing raw to bronze. | Loads a file/table source to bronze with audit. | M | Must | ING-002 | Data Engineer | Build (Paid) | Not Started
ING-011 | Ingestion Framework | Batch Load | Incremental | Batch incremental load with watermark | High-water-mark tracking for incremental pulls. | Only new/changed records loaded; watermark persisted. | M | Must | ING-010 | Data Engineer | Build (Paid) | Not Started
ING-012 | Ingestion Framework | Batch Load | Declarative | Declarative batch ingestion (Lakeflow DP) | Batch ingestion expressed as a declarative pipeline. | Declarative pipeline lands bronze; parity with non-declarative. | M | Must | ING-002 | Data Engineer | Build (Paid) | Not Started
ING-020 | Ingestion Framework | Stream Load | File streaming | Auto Loader streaming to bronze | Incremental file streaming via Auto Loader (non-declarative). | Streams files to bronze with checkpointing. | M | Must | ING-002 | Data Engineer | Build (Paid) | Not Started
ING-021 | Ingestion Framework | Stream Load | Declarative stream | Declarative streaming table (Lakeflow DP) | Streaming table with optional real-time mode. | Declarative streaming ingestion runs; bounded latency. | M | Should | ING-012 | Data Engineer | Build (Paid) | Not Started
ING-022 | Ingestion Framework | Stream Load | Message bus | Message-bus connector (Kafka/Kinesis/EventHub) | Streaming ingestion from message buses. | Consumes from a topic to bronze (paid; FE has no external access). | M | Could | ING-020 | Data Engineer | Build (Paid) | Not Started
ING-030 | Ingestion Framework | Load Patterns | Append | Append load pattern | Append-only landing for immutable/event data. | Appends without duplication; idempotent reruns. | S | Must | ING-010 | Data Engineer | Build (Paid) | Not Started
ING-031 | Ingestion Framework | Load Patterns | SCD2 | SCD2 load pattern | Declarative APPLY CHANGES and non-declarative MERGE variants. | SCD2 history correct for inserts/updates/deletes; both engines. | L | Must | ING-030 | Data Engineer | Build (Paid) | Not Started
ING-040 | Ingestion Framework | Source Connectors | CDC | Lakeflow Connect CDC config (DB sources) | CDC from policy/claims systems (Guidewire/Duck Creek) on paid. | CDC ingests changes with lineage in Unity Catalog. | L | Should | ING-002 | Data Engineer | Build (Paid) | Not Started
ING-041 | Ingestion Framework | Source Connectors | Synthetic data | Synthetic P&C source generator (PoC) | Generate policy/claims/payment files for Free Edition benchmark. | Realistic synthetic feeds available in cloud storage. | M | Must | FND-004 | Data Engineer | PoC-Benchmark (Free) | Not Started
ING-050 | Ingestion Framework | Resilience | Schema drift | Schema drift detection + handling | Detect source schema changes; evolve or quarantine. | Drift detected; configurable evolve/quarantine action. | M | Should | ING-031 | Data Engineer | Build (Paid) | Not Started
ING-051 | Ingestion Framework | Resilience | Error handling | Dead-letter / quarantine + replay | Route bad records to quarantine and support replay. | Bad records quarantined; replay reprocesses cleanly. | M | Should | ING-031 | Data Engineer | Build (Paid) | Not Started
ING-052 | Ingestion Framework | Resilience | ABC hooks | ABC instrumentation for ingestion | Emit audit + balance (row counts) per ingestion run. | Run logged; source/target counts captured for recon. | S | Must | FND-011 | Data Engineer | Build (Paid) | Not Started
HARM-001 | Harmonization / Curation Framework | Engine Abstraction | Framework design | Spec: harmonization framework (.md) | Transform engine, layers, SCD, latency, mapping contract. | Spec approved; covers silver and gold, declarative/non-declarative. | S | Must | FND-001 | Architect | Foundation | Not Started
HARM-002 | Harmonization / Curation Framework | Engine Abstraction | Transform engine | Transform engine abstraction (SQL + Spark) | Support query-based and Spark-API transforms via one config. | Both transform styles run from config. | M | Must | HARM-001 | Architect | Build (Paid) | Not Started
HARM-010 | Harmonization / Curation Framework | Standardization & Cleansing | UDF framework | UDF registry framework (SQL + Spark) | Register/version reusable UDFs callable from config. | UDFs registered and invoked by config. | M | Must | HARM-002 | Data Engineer | Build (Paid) | Not Started
HARM-011 | Harmonization / Curation Framework | Standardization & Cleansing | Standardization | Standardization UDF library | Dates, codes, currency, address standardization UDFs. | Standard formats applied; tested on samples. | M | Must | HARM-010 | Data Engineer | Build (Paid) | Not Started
HARM-012 | Harmonization / Curation Framework | Standardization & Cleansing | Cleansing | Cleansing UDF library | Null handling, format fixes, dedup, validation UDFs. | Cleansing rules applied; measurable quality lift. | M | Must | HARM-010 | Data Engineer | Build (Paid) | Not Started
HARM-020 | Harmonization / Curation Framework | Mapping | Source-to-target | Source-to-target mapping config + applier | Mapping engine bronze to silver to gold. | Mappings drive transforms; outputs match spec. | L | Must | HARM-002 | Data Engineer | Build (Paid) | Not Started
HARM-021 | Harmonization / Curation Framework | Mapping | Canonical model | Conform to ACORD-aligned canonical model | Map to party/policy/coverage/claim/payment/loss entities. | Silver conforms to canonical schema. | L | Should | HARM-020 | Data Engineer | Build (Paid) | Not Started
HARM-030 | Harmonization / Curation Framework | Engine Modes | Declarative | Declarative curation (Lakeflow DP) | Materialized views / streaming tables for silver/gold. | Declarative curation runs; parity with non-declarative. | M | Must | HARM-002 | Data Engineer | Build (Paid) | Not Started
HARM-031 | Harmonization / Curation Framework | Engine Modes | Non-declarative | Non-declarative curation (batch + streaming + MERGE) | Custom Spark transforms with MERGE for upserts. | Non-declarative path runs; results match. | M | Must | HARM-002 | Data Engineer | Build (Paid) | Not Started
HARM-040 | Harmonization / Curation Framework | Latency | Micro-batch | Micro-batch processing mode | Scheduled micro-batch curation. | Micro-batch runs at configured interval. | S | Must | HARM-031 | Data Engineer | Build (Paid) | Not Started
HARM-041 | Harmonization / Curation Framework | Latency | Near real-time | Near-real-time mode | Low-latency / real-time mode curation. | Sub-minute latency on streaming path (paid/scale). | M | Could | HARM-030 | Data Engineer | Build (Paid) | Not Started
HARM-050 | Harmonization / Curation Framework | SCD & Layers | SCD1 | SCD1 pattern | Overwrite-on-change dimension handling. | SCD1 produces latest-state correctly. | M | Must | HARM-020 | Data Engineer | Build (Paid) | Not Started
HARM-051 | Harmonization / Curation Framework | SCD & Layers | SCD2 | SCD2 pattern | History-preserving dimension handling. | SCD2 versions correct across changes. | M | Must | HARM-050 | Data Engineer | Build (Paid) | Not Started
HARM-052 | Harmonization / Curation Framework | SCD & Layers | Append | Append pattern | Append fact/event rows. | Appends without duplication. | S | Must | HARM-020 | Data Engineer | Build (Paid) | Not Started
HARM-053 | Harmonization / Curation Framework | SCD & Layers | Gold marts | Gold-layer marts builder | Build claims, underwriting/policy, customer-360 marts. | Gold marts populated from silver per spec. | L | Should | HARM-021 | Data Engineer | Build (Paid) | Not Started
HARM-054 | Harmonization / Curation Framework | SCD & Layers | ABC hooks | ABC instrumentation for harmonization | Emit audit + balance per curation run. | Run logged; counts/control totals captured. | S | Must | FND-011 | Data Engineer | Build (Paid) | Not Started
DQ-001 | Data Quality Framework | Rule Definition | Framework design | Spec: DQ framework (.md) | Rule schema, scopes, at-rest/in-motion, actions, monitoring. | Spec approved; covers warn/block/quarantine. | S | Must | FND-001 | Architect | Foundation | Not Started
DQ-002 | Data Quality Framework | Rule Definition | Rule model | DQ rule model + config tables | Rule, scope, threshold, severity, action metadata. | Rules definable via config; validated. | M | Must | DQ-001 | Data Engineer | Build (Paid) | Not Started
DQ-010 | Data Quality Framework | In-Motion | Declarative | In-motion DQ via DLT expectations | Expectations on declarative pipelines. | Expectations enforce rules during flow. | M | Must | DQ-002 | Data Engineer | Build (Paid) | Not Started
DQ-011 | Data Quality Framework | In-Motion | Non-declarative | In-motion DQ for non-declarative path | Inline checks within Spark transforms. | Rules enforced inline; failures captured. | M | Must | DQ-002 | Data Engineer | Build (Paid) | Not Started
DQ-020 | Data Quality Framework | At-Rest | Monitoring | At-rest DQ via Lakehouse Monitoring | Profiles + metrics on landed tables. | Monitors produce profile + drift metrics. | M | Should | DQ-002 | Data Engineer | Build (Paid) | Not Started
DQ-030 | Data Quality Framework | Actions | Action engine | Action engine: warn / block / quarantine | Configurable action semantics per rule severity. | Each action behaves per spec; logged. | M | Must | DQ-010 | Data Engineer | Build (Paid) | Not Started
DQ-031 | Data Quality Framework | Actions | Quarantine | Quarantine store + reprocess | Route failing records and support reprocessing. | Quarantine populated; reprocess clears valid records. | M | Should | DQ-030 | Data Engineer | Build (Paid) | Not Started
DQ-040 | Data Quality Framework | Monitoring | Reporting | DQ results to ABC + DQ dashboard | Persist DQ outcomes to ABC; build monitoring dashboard. | Dashboard shows pass/fail trends by rule/feed. | M | Must | DQ-030 | Data Engineer | Build (Paid) | Not Started
DQ-041 | Data Quality Framework | Monitoring | Quality | DQ rule unit tests + fixtures | Tests for rule evaluation and actions. | Rule tests pass for pass/fail/edge cases. | M | Should | DQ-030 | QA | Build (Paid) | Not Started
REC-001 | Reconciliation Framework | Design | Framework design | Spec: reconciliation framework (.md) | Recon types, tolerances, source-of-record, ABC Balance link. | Spec approved; covers count + financial control totals. | S | Must | FND-001 | Architect | Foundation | Not Started
REC-002 | Reconciliation Framework | Design | Rule model | Recon rule model + config | Count, control-total, cross-layer, source-of-record, tolerance. | Recon rules definable via config. | M | Must | REC-001 | Data Engineer | Build (Paid) | Not Started
REC-010 | Reconciliation Framework | Checks | Counts | Row-count reconciliation across layers | Source/bronze/silver/gold count balancing. | Count breaks detected within tolerance. | M | Must | REC-002 | Data Engineer | Build (Paid) | Not Started
REC-011 | Reconciliation Framework | Checks | Control totals | Financial control-total reconciliation | Premium/claim/payment sum balancing across layers. | Amount breaks detected and reported. | M | Must | REC-002 | Data Engineer | Build (Paid) | Not Started
REC-012 | Reconciliation Framework | Checks | Tolerance | Tolerance + break classification | Thresholds and severity classification for breaks. | Breaks classified; within-tolerance passes. | S | Should | REC-010 | Data Engineer | Build (Paid) | Not Started
REC-020 | Reconciliation Framework | Reporting | ABC Balance | Recon results to ABC Balance + dashboard | Persist recon to ABC Balance; build recon dashboard. | Dashboard shows breaks by feed/layer. | M | Must | REC-011 | Data Engineer | Build (Paid) | Not Started
REC-021 | Reconciliation Framework | Reporting | Investigation | Recon break investigator hooks | Drill to differing keys/amounts across layers. | Analyst can trace a break to records. | M | Could | REC-012 | Data Engineer | Build (Paid) | Not Started
MASK-001 | Data Masking | Design | Framework design | Spec: masking framework (.md) | Classification, policy, technique (dynamic vs physical). | Spec approved; covers PII/PHI handling. | S | Must | FND-001 | Architect | Foundation | Not Started
MASK-002 | Data Masking | Classification | PII tagging | PII/PHI classification + UC tagging | Classify sensitive columns and tag in Unity Catalog. | Sensitive columns tagged; catalog reflects tags. | M | Must | MASK-001 | Architect | Build (Paid) | Not Started
MASK-010 | Data Masking | Techniques | Dynamic | Dynamic masking via UC column/row masks | Column masks + row filters (ABAC) at read. | Unauthorized users see masked values. | M | Must | MASK-002 | Data Engineer | Build (Paid) | Not Started
MASK-011 | Data Masking | Techniques | Physical | Physical masking: tokenize/hash at write | Reversible tokenization and irreversible hashing. | Configured columns tokenized/hashed at write. | M | Should | MASK-002 | Data Engineer | Build (Paid) | Not Started
MASK-020 | Data Masking | Policy | Applier | Metadata-driven masking applier | Apply masking based on classification + policy config. | Masking applied per config across layers. | M | Must | MASK-010 | Data Engineer | Build (Paid) | Not Started
MASK-021 | Data Masking | Policy | Audit | Masking + access audit to ABC | Audit masking application and sensitive-data access. | Masking and access events logged for compliance. | S | Should | MASK-020 | Data Engineer | Build (Paid) | Not Started
AGENT-001 | Agentic Solution | Architecture | Design | Spec: agentic solution architecture (.md) | Tools, Genie Code vs Agent Bricks, HITL, audit, guardrails. | Spec approved; defines build-time vs run-time skills. | M | Must | FND-001 | Architect | Foundation | Not Started
AGENT-002 | Agentic Solution | Architecture | Govern loop | Govern loop: HITL + feedback + audit | Approval workflow, feedback capture, agent audit trail to ABC. | Every agent action approved + logged; feedback stored. | M | Must | AGENT-001 | ML/AI Engineer | Build (Paid) | Not Started
AGENT-003 | Agentic Solution | Architecture | Router / Supervisor | Router / Supervisor agent (Agent Bricks) | Genie supervisor that classifies intent and routes to framework-dev / authoring / runtime / interaction skills in dependency order, govern-looped and ABC-logged. | Routes a build/onboard/operate request to the correct skills in order; HITL-gated; logged to ABC. | L | Must | AGENT-002 | ML/AI Engineer | Build (Paid) | Not Started
AGENT-010 | Agentic Solution | Build-time Skills | Metadata population | Metadata population skill | Profile a source and draft ingestion/harmonization config. | Agent drafts valid config; human approves. | L | Must | AGENT-002 | ML/AI Engineer | Build (Paid) | Not Started
AGENT-011 | Agentic Solution | Build-time Skills | Mapping | Source-to-target mapping suggestion | Propose mappings using schema + profiling + canonical model. | Suggested mappings accepted with edits. | L | Should | AGENT-010 | ML/AI Engineer | Build (Paid) | Not Started
AGENT-012 | Agentic Solution | Build-time Skills | Code-gen | Transformation code-generation skill | Generate SQL/Spark transforms from mapping. | Generated code runs and passes tests. | L | Should | AGENT-011 | ML/AI Engineer | Build (Paid) | Not Started
AGENT-013 | Agentic Solution | Build-time Skills | DQ rules | DQ rule suggestion skill | Propose DQ rules + thresholds from profiles. | Suggested rules reviewed and deployed. | M | Should | AGENT-010 | ML/AI Engineer | Build (Paid) | Not Started
AGENT-014 | Agentic Solution | Build-time Skills | Recon rules | Reconciliation rule generation skill | Propose count and control-total recon checks. | Suggested recon rules accepted. | M | Could | AGENT-010 | ML/AI Engineer | Build (Paid) | Not Started
AGENT-015 | Agentic Solution | Build-time Skills | Masking | PII + masking-policy suggestion skill | Classify PII and suggest masking policy/config. | Classification reviewed; policy generated. | M | Should | AGENT-010 | ML/AI Engineer | Build (Paid) | Not Started
AGENT-016 | Agentic Solution | Build-time Skills | Testing | Test + synthetic-data generation skill | Generate unit tests and edge-case data. | Generated tests run; data covers edge cases. | M | Could | AGENT-010 | ML/AI Engineer | Build (Paid) | Not Started
AGENT-017 | Agentic Solution | Build-time Skills | Docs | Documentation/data-dictionary skill | Generate data dictionary, lineage notes, runbooks. | Docs generated from metadata + catalog. | M | Could | AGENT-010 | ML/AI Engineer | Build (Paid) | Not Started
AGENT-020 | Agentic Solution | Run-time Skills | Triage | Failure triage / RCA skill | Read DLT event log + ABC exceptions; diagnose failures. | Agent proposes correct root cause on test cases. | L | Should | AGENT-002 | ML/AI Engineer | Build (Paid) | Not Started
AGENT-021 | Agentic Solution | Run-time Skills | Self-heal | Self-healing / auto-rerun | Retry, reprocess micro-batches, quarantine-and-replay. | Recovers from transient failures within guardrails. | L | Could | AGENT-020 | ML/AI Engineer | Build (Paid) | Not Started
AGENT-022 | Agentic Solution | Run-time Skills | Anomaly | Anomaly & schema-drift detection | Watch ABC audit + system tables for anomalies/drift. | Alerts raised on volume/latency/drift anomalies. | M | Could | AGENT-020 | ML/AI Engineer | Build (Paid) | Not Started
AGENT-030 | Agentic Solution | Interaction | NL authoring | NL pipeline authoring (Genie Code) | Natural-language to config draft via Genie Code. | NL request yields valid config draft. | M | Should | AGENT-010 | ML/AI Engineer | Build (Paid) | Not Started
AGENT-031 | Agentic Solution | Interaction | Ops Q&A | Ops Q&A Genie space over ABC | Genie space answering operational questions over ABC + system tables. | Common ops questions answered correctly. | M | Should | FND-011 | ML/AI Engineer | Build (Paid) | Not Started
AGENT-032 | Agentic Solution | Interaction | Impact | Impact / lineage analysis skill | Answer downstream-impact questions using UC lineage. | Impact answers match lineage graph. | M | Could | AGENT-031 | ML/AI Engineer | Build (Paid) | Not Started
AGENT-040 | Agentic Solution | Migration | Legacy ETL | Legacy ETL to framework migration agent | Translate legacy notebooks/ETL into config + Spark/SQL. | Migrated unit produces equivalent output. | XL | Could | AGENT-012 | ML/AI Engineer | Build (Paid) | Not Started
AGENT-050 | Agentic Solution | RAG | Knowledge | Vector Search + RAG over policy docs | Index policy/coverage docs; RAG Q&A (single endpoint on FE). | RAG answers grounded in indexed docs. | M | Could | AGENT-002 | ML/AI Engineer | Build (Paid) | Not Started
FINOPS-001 | FinOps & Cost Management | Design | Methodology | Spec: FinOps cost + estimation model (.md) | Consumption metrics, unit-cost method, estimation approach. | Spec approved; methodology agreed. | M | Must | FND-001 | FinOps/Analyst | Foundation | Not Started
FINOPS-002 | FinOps & Cost Management | Consumption | Capture | Consumption capture via ABC Cost-Tracking | Aggregate DBU/time/Genie-session metrics from ABC. | Consumption available per run/component. | M | Must | FND-022 | FinOps/Analyst | Build (Paid) | Not Started
FINOPS-003 | FinOps & Cost Management | Consumption | Billing tables | system.billing.usage ingestion (paid) | Pull genie-tagged + SKU usage into a cost mart. | Cost mart reflects billable usage by tag/SKU. | M | Should | FINOPS-002 | FinOps/Analyst | Build (Paid) | Not Started
FINOPS-010 | FinOps & Cost Management | Unit Cost | Computation | Unit-cost computation | Cost per feed / transform / Genie generation / run. | Unit costs computed from consumption + list price. | M | Must | FINOPS-002 | FinOps/Analyst | Build (Paid) | Not Started
FINOPS-020 | FinOps & Cost Management | Dashboard | FinOps dashboard | FinOps dashboard (AI/BI) | Genie vs warehouse DBUs, cost by component/feed/run, trend, unit cost. | Dashboard live; cost views match cost mart. | L | Must | FINOPS-010 | FinOps/Analyst | Build (Paid) | Not Started
FINOPS-030 | FinOps & Cost Management | Estimation | Customer model | Customer probable-cost estimation model (xlsx) | Drivers x list price x scenario bands (low/expected/high). | Model outputs probable cost with bands; no formula errors. | L | Must | FINOPS-010 | FinOps/Analyst | Build (Paid) | Not Started
FINOPS-031 | FinOps & Cost Management | Estimation | Pricing | Pricing assumptions sheet | Post-July-2026 Genie pricing + SQL/pipeline DBU rates + region. | Assumptions documented and adjustable. | S | Must | FINOPS-030 | FinOps/Analyst | Build (Paid) | Not Started
FINOPS-040 | FinOps & Cost Management | Estimation | Scorecard | Benchmark cost scorecard | Link PoC consumption to projected customer cost. | Scorecard maps PoC unit costs to customer estimate. | M | Should | FINOPS-010 | FinOps/Analyst | PoC-Benchmark (Free) | Not Started
OBS-001 | Observability | Design | Design | Spec: observability (.md) | Logging, tracing, metrics model across frameworks. | Spec approved; metrics defined. | S | Should | FND-001 | Architect | Foundation | Not Started
OBS-010 | Observability | Logging | Tracing | Centralized logging + trace IDs | Correlated logs across frameworks to ABC + event log. | Traces span ingestion to gold for a run. | M | Must | FND-023 | Data Engineer | Build (Paid) | Not Started
OBS-011 | Observability | Metrics | Performance | Performance metrics capture | Run duration, throughput, latency metrics. | Metrics captured per run; queryable. | M | Should | OBS-010 | Data Engineer | Build (Paid) | Not Started
OBS-020 | Observability | Monitoring | Dashboard | Operational monitoring dashboard | Pipeline health, freshness, SLA tracking. | Dashboard shows health and freshness. | M | Should | OBS-010 | Data Engineer | Build (Paid) | Not Started
DEVOPS-001 | CI/CD & DevOps | Design | Design | Spec: CI/CD + deployment (.md) | Asset Bundles, environments, promotion strategy. | Spec approved. | S | Must | FND-030 | Platform/DevOps | Foundation | Not Started
DEVOPS-010 | CI/CD & DevOps | IaC | Bundles | Databricks Asset Bundles for all assets | Bundle config, pipelines, jobs as IaC. | Bundle deploys the framework to a workspace. | L | Must | DEVOPS-001 | Platform/DevOps | Build (Paid) | Not Started
DEVOPS-011 | CI/CD & DevOps | IaC | Promotion | Environment promotion + secrets mgmt | dev/test/prod promotion and secret/connection handling. | Promotion works across envs; secrets secured. | M | Should | DEVOPS-010 | Platform/DevOps | Hardening (Paid) | Not Started
DEVOPS-012 | CI/CD & DevOps | Pipelines | CI | CI: lint + unit tests (no wheel) | Continuous integration for the framework source. | CI green on PRs; source validated. | M | Must | FND-032 | Platform/DevOps | Foundation | Not Started
DEVOPS-013 | CI/CD & DevOps | Pipelines | CD | CD: deploy bundles + smoke tests | Continuous deployment with post-deploy smoke tests. | Deploys validated by smoke tests. | M | Should | DEVOPS-010 | Platform/DevOps | Hardening (Paid) | Not Started
BENCH-001 | PoC Benchmark Harness | Design | Plan | Spec: benchmark plan + success metrics | Define metrics: spec->Genie-Code fidelity and functional correctness. | Benchmark plan approved; metrics measurable. | S | Must | FND-001 | Architect | Foundation | Not Started
BENCH-002 | PoC Benchmark Harness | Setup | Free Edition | Free Edition workspace setup | UC metastore, SQL warehouse, serverless on Free Edition. | Workspace ready; Genie Code available. | S | Must | - | Platform/DevOps | PoC-Benchmark (Free) | Not Started
BENCH-010 | PoC Benchmark Harness | Slice | Vertical slice | Thin vertical slice: ingest to mask | One feed: ingest -> harmonize -> DQ -> recon -> mask on Free Edition. | Slice runs end to end on synthetic data. | L | Must | ING-001,HARM-001,DQ-001,REC-001,MASK-001,ING-041,BENCH-002 | Data Engineer | PoC-Benchmark (Free) | Not Started
BENCH-011 | PoC Benchmark Harness | Slice | Genie generation | Generate slice via Genie Code from specs | Use specs + metadata-population agent; capture generation metrics. | Slice generated by Genie Code; metrics recorded. | M | Must | BENCH-010,AGENT-010 | ML/AI Engineer | PoC-Benchmark (Free) | Not Started
BENCH-012 | PoC Benchmark Harness | Validation | Correctness | Functional-correctness validation | Compare generated outputs against golden results. | Outputs match golden set; deltas explained. | M | Must | BENCH-011 | QA | PoC-Benchmark (Free) | Not Started
BENCH-020 | PoC Benchmark Harness | Scorecard | Results | Benchmark scorecard | Fidelity, effort saved, correctness, consumption summary. | Scorecard produced; informs paid build + estimate. | M | Must | BENCH-011,BENCH-012,FINOPS-010 | Architect | PoC-Benchmark (Free) | Not Started
ENABLE-001 | Specs & Documentation | Specs | Template | Genie-Code-ready spec template + index | Standard .md template and index for all component specs. | Template adopted; specs indexed. | S | Must | FND-001 | Tech Writer | Foundation | Not Started
ENABLE-010 | Specs & Documentation | Docs | Runbooks | Framework documentation + runbooks | User and operations documentation for the frameworks. | Docs cover setup, config, run, troubleshoot. | M | Should | FND-031 | Tech Writer | Enablement | Not Started
ENABLE-011 | Specs & Documentation | Docs | Demo | PoC demo script + walkthrough | Narrative and steps to demo the PoC slice. | Demo script runs cleanly end to end. | S | Could | BENCH-010 | Tech Writer | Enablement | Not Started

## Legend
Legend & Conventions
Columns | Meaning
Task ID | Unique ID, prefixed by component (FND, ING, HARM, DQ, REC, MASK, AGENT, FINOPS, OBS, DEVOPS, BENCH, ENABLE).
Theme (Epic) | Top-level workstream / framework.
Capability (Feature) | Feature group within the epic.
Sub-capability (Story) | Story-level grouping of tasks.
Task | Low-level, actionable unit of work (~0.5-2 days).
Description | What the task delivers.
Acceptance criteria | Definition of Done for the task.
Size | T-shirt estimate (see sizing key).
Priority | MoSCoW priority.
Dependencies | Predecessor Task IDs (comma-separated).
Owner role | Suggested role; names left blank to assign.
Phase | Delivery stage / where it runs (see phases).
Status | Workflow status (default Not Started).
Size (T-shirt) | Guide
S | Small (~0.5-1 day)
M | Medium (~1-3 days)
L | Large (~3-5 days)
XL | Extra-large (~1-2 weeks; consider splitting)
Priority (MoSCoW) | Meaning
Must | Required for a working framework / PoC
Should | Important, not vital for first cut
Could | Desirable if time permits
Won't | Out of scope for now
Phase | Meaning
Foundation | Shared groundwork incl. portable .md specs (authored in Cowork; edition-neutral).
PoC-Benchmark (Free) | Runs on Databricks Free Edition to benchmark spec->Genie-Code fidelity + functional correctness.
Build (Paid) | Full framework build on the paid workspace from the same specs.
Hardening (Paid) | Productionization: promotion, secrets, CD, scale.
Enablement | Documentation, demo and runbooks.
Notes
Specs (.md) are the portable IP: authored in Claude Cowork, used to benchmark on Free Edition, then reused to build on the paid workspace.
Free Edition limits: serverless only, one active pipeline per type, 5 concurrent job tasks, one 2X-Small SQL warehouse, limited model serving, restricted outbound internet, daily quotas.
On Free Edition use synthetic data (no live CDC); heavier agentic/serving tasks are 'Build (Paid)'.
FinOps: measure consumption on Free Edition, apply paid list prices (post-6-Jul-2026 Genie pricing), scale by volume = probable customer cost.

## Summary
Backlog Summary
Total tasks | 115
By Epic | Count
Foundation & ABC Modernization | 17
Ingestion Framework | 15
Harmonization / Curation Framework | 16
Data Quality Framework | 9
Reconciliation Framework | 7
Data Masking | 6
Agentic Solution | 19
FinOps & Cost Management | 8
Observability | 4
CI/CD & DevOps | 5
PoC Benchmark Harness | 6
Specs & Documentation | 3
By Phase | Count
Foundation | 26
PoC-Benchmark (Free) | 7
Build (Paid) | 78
Hardening (Paid) | 2
Enablement | 2
By Size | Count
S | 25
M | 72
L | 17
XL | 1
By Priority | Count
Must | 72
Should | 31
Could | 12
Won't | 0